## Overall schedule
Approximate time frame dates based on Conference in April Year 0 (YY), YY-2 is 2 years prior to conference, YY-1 is 1 year prior to conference
Milestone | Lead in time (months) | Approximate time frame | Conference committee | ISB Executive Committee (ISB-EC) or ISB officer
Issue call for proposals to host the conference | 23 | May 15, YY-2 |  | ISB Executive Committee (ISB-EC)
Deadline for application to host the conference | 20 | Mid-August, YY-2 |  | ISB-EC
Announcement of hosting institution | 19 | September 1, YY-2 |  | ISB-EC
Names of ISB-EC observers provided to Biocuration Organising Committee | 19 | September 1, YY-2 | Chair(s) | ISB-EC
Establish Organising Committee | 16 | December 1, YY-2 | Chair(s)
Develop sponsorship plan | 16 | December 1, YY-2 | Organizing Committee (OC)
Start grant writing (optional) | 15 | January 1, YY-1 | OC
Conference theme or tag line finalised | 13 | March 1, YY-1 | OC
Conference budget finalised | 12 | April 15, YY-1 | Chair(s), Treasurer
Finalize contract with conference venue | 12 | April 15, YY-1 | OC
Annnouncement of Conference Venue to ISB Membership | 12 | April, YY-1 | OC | ISB-EC
Begin contact with potential sponsors | 12 | April, YY-1 | OC
Release conference website | 12 | April, YY-1 | OC
Annnouncement of Conference website to ISB Membership via link to conference website on ISB website and ISB mailing list etc | 12 | April, YY-1 |  | ISB-EC
Contact DATABASE to discuss deadline for Submissions for Biocuration Virtual Issue | 12 | April, YY-1 | OC
Scientific Committee selected | 12 | April, YY-1 | OC | ISB-EC
Scientific Committee Invited | 12 | April, YY-1 | OC | ISB-EC
Begin discussions about Keynote speakers | 12 | April, YY-1 | Scientific Committee (SC)
Keynote speakers selected and invited |  | June, YY-1 | SC
Define Scientific Sessions for Conference | 7.5 | Aug 15, YY-1 | SC
Announcement Call for Submission for Biocuration Virtual Issue DATABASE | 7.5 (or earlier) | Aug 15, YY-1 | OC
Call for volunteers from institution(s) (optional) | 7 | Sep 1, YY-1 | OC
Agenda overview (with scientific sessions) posted on website | 7 | Sep 1, YY-1 | OC
Announce sponsorship package options on conference website | 7 | Sep 1, YY-1 | OC
Open Call for workshop sessions; send announcement | 7 | Sep 20, YY-1 | OC
Finalise sponsorships | 7 | Sep 20, YY-1 | OC
Travel Fellowship Committee (TFC) selected = 2 member of SC + ISB Award Chair | 6 | Oct 1, YY-1 | SC | ISB-EC-Award chair
Set up forms for Travel Fellowship applications | 6 | Oct 1, YY-1 | Travel Fellowships Committee (TFC)
Add link to Travel Fellowship application forms to ISB and Conference websites | 6 | Oct 1, YY-1 | OC | ISB-EC
Add link to ISB membership application to registration form | 6 | Oct 1, YY-1 | OC
Registration and application for travel fellowships opens; send announcement | 6 | Oct 1, YY-1 | OC
Open Call for Talks and posters abstracts; send announcement to ISB mailing list | 6 | Oct 1, YY-1 | OC
Promote Conference details/deadlines ISB Membership via link to conference website on ISB website and ISB mailing list etc | 6 | Oct 1, YY-1 |  | ISB-EC
Deadline for submitting papers for Biocuration Virtual Issue DATABASE (Date to be confirmed) | 5 | Oct 31, YY-1 | OC
Travel Fellowship application deadline (before abstract submission deadline) | 5 | Nov 1, YY-1 | TFC
check on Database issue submissions and make sure authors submit an abstract as well | 5 | Nov 7, YY-1 | SC
Send reminder about early bird registration deadline | 5 | Nov 15, YY-1 | OC | ISB-EC
Send 1st reminder about requesting travel visas | 5 | Nov 15, YY-1 | OC | ISB-EC
Travel Fellowship applicants selected | 5 | Nov 15, YY-1 | TFC
Travel Fellowship applicants notified | 4 | Dec 1, YY-1 | TFC
Early bird registration deadline | 4 | Dec 1, YY-1 | OC
Session abstract submission deadline | 3.5 | Dec 15, YY-1 | SC
Workshop sessions submission deadline | 3.5 | Dec 15, YY-1 | SC
Sessions abstract selection notices sent to presenters | 2.5 | Jan 15, YY | SC
Early Registration Deadline | 2 | 1 Feb, YY | OC
Send 2nd reminder about requesting travel visas | 2 | Feb 1, YY | OC | ISB-EC
Send early bird registration reminder to ISB mailing list and to paper/abstract submitters | 2.5 | Jan 15, YY | OC | ISB-EC
Late Poster abstract deadline | 1.5 | Feb 15, YY | SC
Inform late abstract submitters of outcome of talk/poster |  |  | SC
Provide presenters with poster size/number/talk time details | 1.75 | Feb 20, YY | OC
Final agenda sent to OC | 1 | Early March, YY | SC
Promote Conference details and final registration deadline | 1 | Early March, YY | OC | ISB-EC
Finalize Staffing Plan - volunteers, mic runners, AV teams, etc. | 0.5 | Mar 15, YY | OC
Final agenda posted to website | 0.25 | Late March, YY | OC
Final registration deadline | 0.25 | Late March, YY | OC
Conference | 0 | April, YY
Post Conference Survey (Optional) |  | Late April, YY |  | ISB-EC
YY = Year of the conference |  |  |  | ISB-EC = ISB Executive Committee
YY-1 = one year prior to conference date |  |  |  | OC = Organizing Committee
YY-2 = two years prior to conference date |  |  |  | SC = Scientific Committee
Travel fellowships should open with registration and be open for at least 1 month. Recipients should be notified 2 weeks after the closing date and at least 4 months before conference starts to allow time for visa applications. |  |  |  | TFC = Travel Fellowships Committee